## Blad1
level | risk specification | risk estimation | mitigation | monitoring
User level | Low involvement of users. Not interested in new tech/solution, do not consider the "problem" substantial enough to want a solution for it. Not interested in learning how to use it. |  | MOM-test. Prototyping to ensure simple, easy to use UI, good fit for the problem. Exclusive offers to attract customers. | Prototype to get feedback
| Low interest from businesses. Perceive gains as small compared to work required. Not willing to learn new technology. |  | Prioritize simple and quick maintenance on business-end. Integration into their WMS. Prototyping. On site support to set up. Offer training to staff. | Prototype to get feedback
Requirement gathering | Requirements not deliverable: cannot get precise enough indoor location services for mapping |  | Early testing. Adjust plan? Plan for alternative solution. | Research before starting implementation
| Misunderstanding/incomplete requirements. Misunderstood MOM-test results, and prospective users expect something other than what we have in mind. Missing important requirement for users to adopt our solution. Unspoken requirements: Do not want to create yet another account, do not wish to see a bunch of ads (which are part of our generating revenue). |  | Prototyping, feedback including ads. | Prototype to get feedback
Planning | Unrealistic schedule and budget, unrealistic goals. Inexperienced team leads to overestimation of our skills and an unrealistic timeplan. |  | Leave extra room. Planning poker to estimate effort for different activities. If possible aqcuire a business-mentor to help and give feedback on how realistic our plan is. | Regular check-ins with timeplan
| Poor planning. Not detailed enough/ insufficient granularity. Missed or overlooked steps. |  | SPM-tools to try and develop a more detailed plan to minimize risk of missing something important. Planning poker: if large variation in estimated effort, or large effort for a given task, perhaps a sign it can (should) be broken down further? | Regular check-ins with timeplan
Analysis | Faulty cost-benefit analysis: planned development of a minor feature turns out to be much more expensive than initially expected |  | Periodic revisions of the plan and reprioritizing items. Using a fine granularity when planning to clarify what needs to get done. | Regular check-ins with timeplan
Design | Lack of integrity in design elements, bad or difficult to use UI |  | Perform prototyping to get user feedback on UI | Prototype to get feedback
| Lack of proper architectural design and plan |  | Separate activity to plan proper architecture. Create structure documents, UML-diagrams, and design meetings with team to ensure everyone is on board. Document structure. | Periodic code reviews
Implementation | Risk for bugs |  | Test first, clean branch with only working code to ensure no broken code contaminates the working space. Internal code reviews. | Periodic code reviews, continous testing
| Lack of proper documentation and comments, difficult to understand for other team-members |  | Plan and create clear guidelines on documentation for produced code. Periodic internal code reviews. | Periodic code reviews
| Lack of necessary skills |  | Clear resource planning to ensure the best fit between resource and task. Team standup-meetings to quickly discover if there is a problem, so that resources may be redistributed. | Team check-ins
Maintenance | Lack of proper documentation |  | Clear guidelines on documentation. Internal code reviews regularly. | Periodic code reviews, continous testing
| Incomplete user documents, too complex for businesses to maintain. |  | Prototyping business side UI, get feedback on documentation, offer ongoing support. Already in planning stage plan for integration into existing WMS to minimize necessary effort from businesses to maintain. | Pre-release feedback
| Political or legal changes that have a negative impact |  | Alternative ways of generating revenue if laws on gathering user data tightens for example | Monitor politics and news in relevant sector